## style 1
Start date | 2021-09-13
Project duration | 30 ECTS | 840 |  | hrs | 21 | weeks
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Task | Start | duration | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31
Start master thesis form & approval | 0 | 1
Notify secretary office/arrange desk | 1 | 1
Topic selection | 1 | 1
Reading literature | 2 | 2
research question and hypotheses | 3 | 1
Writing draft introduction | 2 | 3
Research proposal | 5 | 2
Experimental design | 5 | 2
Experimental setup | 7 | 2
Interim presentation | 9 | 1
Programming | 7 | 3
Testing | 9 | 1
Archie: Experiment proposal | 7 | 1
Lab reservation & time schedule | 8 | 1
PPDB: invitation e-mail & inviting participants | 9 | 1
Running experiment | 10 | 3
Writing draft methods | 10 | 3
Organising data | 13 | 2
Making graphs | 14 | 2
Statistical tests | 15 | 2
Writing results section | 13 | 4
Writing discussion and conclusions | 17 | 1
End master thesis form | 18 | 2 | bar: 0
Finalising report (title page, abstract) | 18 | 2
Final presentation | 20 | 1 | bar: 0
Press release | 21 | 1

## style 2
Start date | 2021-09-13
Project duration | 30 ECTS | 840 |  | hrs / | 40 | hrs per week = |  | 21 | weeks
| style | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Task | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31
Start master thesis form & approval
Topic selection
Reading literature
research question and hypotheses
Writing draft introduction
Research proposal
Experimental design
Experimental setup
Interim presentation
Programming
Testing
Archie: Experiment proposal
Lab reservation & time schedule
PPDB: invitation e-mail & inviting participants
Running experiment
Writing draft methods
Organising data
Making graphs
Statistical tests
Writing results section
Writing discussion and conclusions
End master thesis form
Finalising report (title page, abstract)
Final presentation
Press release